## Project Risk Management Plan
CARECONNECT
PROJECT RISK MANAGEMENT PLAN
RISK | RISK IDENTIFICATION | RISK IMPACT | RISK ASSESSMENT | RISK MITIGATION STRATEGY | SEVERITY
DATA BREACH | PATIENT DATA BREACH |  | POTENTIAL LEGAL ISSUES, TRUST LOST RISK | IMPLEMENT SECURITY, CONDUCT AUDITS, TRAIN STAFF | HIGH
NON COMPLIANCE WITH REGULATION | NON-COMPILANCE WITH HEALTHCARE, DATA PRIVACY RULES |  | SEVERE UNLIKELY PENALTIES WITH COMPLIANCE | CONTINALLY UPDATE POLICIES FOR COMPLIANCE | HIGH
SYSTEM DOWNTIME | UNEXPECTED OUTAGES IMPACT PLATFORM AVAILABILITY |  | HEALTH CARE DISRUPTIONS LIKELY DUE TO TECHNICAL GLITCH | ESTABLISH INFRASTRUCTURE, MAINTAIN REGULARLY PLAN FOR DISASTER RECOVERY | MEDIUM
INEFFECTIVE USER AUTHENTICATION | WEAK AUTHENTICATION LEADS TO UNAUTHORIZED ACCESS |  | HIGH IMPACT LOW CHANCE DUE TO STRONG AUTHENTICATION | REGULARLY UPDATE AND REVIEW AUTHENTICATION METHODS, USE CRYPTOGRAPHICAL MEANS IF REQUIRED | HIGH
POOR USER ADOPTION | INEFFECTIVE USE OF THE PLATFORM BY PROVIDERS OR PATIENTS |  | AFFECT THE PROJECT IMPLENTATION AND UTILIZATION | TRAIN USERS, ADDRESS FEEDBACK, AND AVAIL PLATFORM BENEFITS | MEDIUM
INTEGRATION FAILURE | HINDERANCE TO INTEGRATION BETWEEN PHARMACIES AND INSURANCE SYSTEM |  | DISRUPTION LIKELY DUE TO INCOMPATIBLE SOFTWARE AND POLICIES | WORK WITH STAKEHOLDERS, TEST THOROUGHLY , AND PREPARE BACKUP STRATEGIES | LOW
CLICK HERE TO CREATE IN SMARTSHEET